## Sheet1
Name: Dara Sen
Class: AD400 (Project Management in Software Development)
Assignment: Work Breakdown Structure, Gantt Chart, and Kanban Board
Gantt Chart
| Tasks |  |  | Starting Date | Completion Date | Duration (days)
| Planning | Requirements Definition | Identify core features (products, cart, checkout) | 2026-05-01 | 2026-05-01 | 1
|  |  | Define user roles (customer, admin) | 2026-05-02 | 2026-05-02 | 1
|  | Technology Selection | Choose frontend (React + Vite) | 2026-05-03 | 2026-05-03 | 1
|  |  | Choose backend/payment (Supabase + Stripe) | 2026-05-04 | 2026-05-04 | 1
| Setup | Project Initialization | Create Vite React Project | 2026-05-05 | 2026-05-05 | 1
|  |  | Install dependencies (Zustand, Supabase, Stripe) | 2026-05-06 | 2026-05-06 | 1
|  | Backend Setup | Create Supabase project | 2026-05-07 | 2026-05-07 | 1
|  |  | Configure environment variable | 2026-05-08 | 2026-05-08 | 1
| Frontend Development | UI Structure | Build navigation bar | 2026-05-09 | 2026-05-09 | 1
|  |  | Setup routing (Home, Product, Cart) | 2026-05-10 | 2026-05-10 | 1
|  | Product Features | Display product list | 2026-05-11 | 2026-05-11 | 1
|  |  | Show product details | 2026-05-12 | 2026-05-12 | 1
|  | Cart System | Implement Zustand store | 2026-05-13 | 2026-05-13 | 1
|  |  | Add/remove items from cart | 2026-05-14 | 2026-05-14 | 1
| Backend (Supabase) | Database Design | Create Products table | 2026-05-15 | 2026-05-15 | 1
|  |  | Create Orders table | 2026-05-16 | 2026-05-16 | 1
|  | Authentication | Implement user signup | 2026-05-17 | 2026-05-17 | 1
|  |  | Implement user login | 2026-05-18 | 2026-05-18 | 1
|  | Data Integration | Fetch products from database | 2026-05-19 | 2026-05-19 | 1
|  |  | Store order data | 2026-05-20 | 2026-05-20 | 1
| Payment Integration | Stripe Setup | Create Stripe account | 2026-05-21 | 2026-05-21 | 1
|  |  | Configure API keys | 2026-05-22 | 2026-05-22 | 1
|  | Checkout Process | Create checkout session | 2026-05-23 | 2026-05-23 | 1
|  |  | Handle payment success response | 2026-05-24 | 2026-05-24 | 1
| Testing & Deployment | Testing | Test user flow | 2026-05-25 | 2026-05-25 | 1
|  |  | Fix bugs | 2026-05-26 | 2026-05-27 | 2
|  | Deployment | Deploy frontend (Vercel) | 2026-05-28 | 2026-05-28 | 1
|  |  | Verify live application | 2026-05-29 | 2026-05-30 | 2